## Feature List
BE 4.0.1 | Released Friday Nov 12th 2010
AS 1.1 | Released Nov 1st week 2010
BE 4.1 | Coherence | ActiveSpace | Status | Owner | Comment
General
Refactoring | √ | √ | done | Suresh
Build | √ | x | partial | Sridhar | Only in 4.AS branch
Packaging | x | x |  | Anil/Release
New Base Edition | x | x |  | Jitesh/Kristin
Pricing | x | x |  | Jitesh/Kristin
Merge | x | x |  | Suresh | Biggest task and errorprone. Should be complete by 11/30
Inference Engine
Cluster |  |  | done | Suresh | Interface done as part of the Refactoring. Stringing implementations and testing
DaoProvider | √ | √ | coherence done | Suresh | AS to be implemented - Expect this to be done by Dec 30.
ObjectTable | √ | √ |  | Suresh | AS Dao provider to be implemented
MetadataCache | √ | √ |  | Suresh
AgentManager | √ | √ |  | Suresh
Policies | √ | √ |  | Suresh
SchedulerCache | x | ↑ |  | Bala | Dec 15th - Critical he is working on Reliance
BackingStore | x | ↑ |  | Vincent/Fatih | Nov 30th
CacheAside | x | ↑ |  | Vincent/Fatih
JDBC | x | ↑ |  | Vincent/Fatih
OracleType | x | ↑ |  | Vincent/Fatih
WriteBehind | x | ↑ |  | Vincent/Fatih
JDBC | x | ↑ |  | Vincent/Fatih
OracleType | x | ↑ |  | Vincent/Fatih
GroupMembershipService | √ | √ |  | Suresh
Policies | √ | √ |  | Suresh
Mediator | √ | √ |  | Suresh
Membership | √ | √ |  | Suresh
Entity | √ | √ |  | Suresh
TopicRegistry | √ | √ |  | Suresh
Entity Subsription | √ | √ |  | Suresh
SequenceManager | x | ↑ |  | Suresh | Coherence related should be done by 11/20
EventTableProvider | x | ↑ |  | Suresh | Coherence related should be done by 11/20
Subscription | x | ↑ |  | Suresh
Ownership | x | ↑ |  | Suresh
Transfer | x | ↑ |  | Suresh
Consuming | x | ↑ |  | Suresh
RecoveryManager | x | ↑ |  | Fatih/Bala | Coherence related should be done by 11/30
RuleFunctionService | x | ↑ |  | Bala | Dec 15th
HotDeployment | x | ↑ |  | Bala | Dec 15th
DataGrid
AgentManager | √ | √ |  | Suresh | Depends on AS DAO provider
Policies | √ | ↑ |  | Suresh
C_xxx functions replacement |  |  |  | Suresh/Ashwin
Limited cache size and other CDD settings |  |  |  | Suresh/Ashwin
Dashboard | x | ↑ |  | Vincent/Anand | Coherence done by Dec 15th - Depends on Merge
Monitoring and Management | x | ↑ |  | Ashwin/NickXu | Expected by Jan 15
Domain Subscription | x | ↑ |  | Ashwin/NickXu
System Metrics management | x | ↑ |  | Ashwin/NickXu
Queries | √ | √ |  | Ashwin | AS expected to be done by Jan 15th
Continous | √ | √ |  | Ashwin
Filtered | √ | √ |  | Ashwin
SnapShot | √ | √ |  | Ashwin
Filtered | √ |  |  | Ashwin | Functionality is 100%, performance may be slower
Indexed | √ |  |  | Ashwin | ↑
QA | X | X |  | Fatih/Hugo | Done by Nov 30th so we can run engineering build
Vmware setup | X | X |  | Fatih/Hugo
Blackbox QA | X | X |  | Fatih/Hugo

## Summary
| Coherence% | ActiveSpaces% | Others%
General | 100 | 100 | 30
Inference Engine | 60 | 0 | 40
DataGrid | 80 | 0 | 80
Dashboard | 40 | 10 | 0
Monitoring and Management | 10 | 10 | 0
Queries | 60 | 30 | 70%
QA | 0 | 0 | 20